Leiden University Faculty of Archaeology

Guidelines for research grant applications by staff Faculty of Archaeology

2021 - 2022

June 2021

To execute new research projects, staff employed at Dutch universities have become increasingly dependent on acquiring research grants from an external funding body (e.g. NWO, KNAW, LUF, EU). The Faculty Board has drawn up the present guidelines to steer you towards timely notification and involvement of Faculty Research Support staff and LURIS, who are there for you to help and assist.

Before submitting to the funding body, all research grant applications >50.000 euro need to be evaluated by the Research Committee, and checked by Faculty Project control and Data management staff. The Research Committee evaluates whether the Faculty is an appropriate host for your research project and advises the Board. Applications presented to the Board without an advice from the Research Committee will not be supported by the Faculty.

Are you working with private and/or social partners (museum, state service, other)? Make sure to make an agreed-by-all written statement before the start of the project. Inform /cc the Board once the collaboration has been documented.

Steps to take and deadlines to consider are:

Step 1 /	At the latest 8 weeks prior to submission deadline of desired funding body

- Discuss your plan(s) with your Department Head. Inform the Research Coordinator.

- Is Faculty (temporary, permanent) embedding required? Contact the Board.

- Visit the Leiden University research support services website of LURIS (Contact: Jorrit Kelder).

Step 2	/	At the latest 6 weeks prior to submission deadline of funding body

- Send the Faculty Research Committee  your research plan (max 600 words) addressing:         1) theme, area, period, research questions (2) wider significance and (societal) relevance,   (3) aims, (4) methodology, (5) motivation for the LU Faculty of Archaeology as the desired host, and explain how your research connects to and benefits the Faculty’s research.

The Research Committee advises the Faculty Board. Green light from the Board?

Step 3	/	At the latest 4 weeks prior to submission deadline of funding body

- A check of your budget is required by the Board. Contact the Faculty Project Controller.

- For Open Access matters: contact the UB Leiden.

- Contact the Information Manager for the Data Management paragraph and GDPR issues.

- Obtain embedding form from the Faculty Board if necessary.

After submitting your application

(i)     Peer reviews from the funding body? LURIS assists in writing a response.

(ii)    Invited for an interview? Coaching may be helpful, contact your Head of Department.

(iii)   Success / Unsuccessful / Withdrawal? Inform the Faculty Board and Research coordinator.